## Sheet1
Skill Area | Task | Possible Resources | Effort/Duration | Dependency | Sprint
UI/Angular
| Screen design | Basavaraj
| Build Screens | Basavaraj
| login | Basavaraj
| search | Basavaraj
| main | Basavaraj
| address change | Basavaraj
| email change | Basavaraj
| phone change | Basavaraj
| join | Basavaraj
| unjoin | Basavaraj
| link | Basavaraj
| unlink | Basavaraj
| Validations | Basavaraj
| Error handling | Basavaraj
| invoke spring APIs | Basavaraj
| Unit Testing | Basavaraj
SOLR
design
Indexing - initial load
indexing - delta changes/CDC
Integrating with UI
Unit Testing
Spring/Spring Boot
| APIs for UI | Ranjit & Zinda
| APIs for MuleSoft | Ranjit & Zinda
| DB updates using Hybernate | Ranjit & Zinda
| Publish to MQ | Ranjit & Zinda
| Transaction Manager | Ranjit & Zinda
| Error Handling | Ranjit & Zinda
| Monitoring CDC | Ranjit & Zinda
| Processing CDC records | Ranjit & Zinda
| ownership add/update/delete | Ranjit & Zinda
| address add/update/delete | Ranjit & Zinda
| phone add/update/delete | Ranjit & Zinda
| email add/update/delete | Ranjit & Zinda
| membership add/update/delete | Ranjit & Zinda
| obl add/update/delete | Ranjit & Zinda
| link/unlink | Ranjit & Zinda
| join/unjoin | Ranjit & Zinda
| Unit Testing | Ranjit & Zinda
Hibernate
| design | Ranjit & Zinda
| Build Objects | Ranjit & Zinda
| ownership | Ranjit & Zinda
| address | Ranjit & Zinda
| email | Ranjit & Zinda
| phone | Ranjit & Zinda
| membership | Ranjit & Zinda
| OBL | Ranjit & Zinda
| Stging tables for delta updates/CDC | Ranjit & Zinda
| Unit Testing | Ranjit & Zinda
MuleSoft
RAML design
API Gateway
Orachestration/flows
ownership add/update/delete
address add/update/delete
phone add/update/delete
email add/update/delete
membership add/update/delete
OBL add/update/delete
Process APIs
- design
- build
- test
System APIS
- design
- build
- test
Publish/Subscribe to MQ
SOLR update
TSW APIs
Universe APIs
XML<->JSON translations (dataweave)
Error Handling
Unit Testing
Database
| create table scripts | Praveen Kumar Morum
| design/create other DB objects (views, triggers, synonyms, indexes/constraints) | Praveen Kumar Morum
| Create core tables | Praveen Kumar Morum
| Create staging tables | Praveen Kumar Morum
| create mapping tables | Praveen Kumar Morum
| Load mapping tables | Praveen Kumar Morum
| Load unique ids | Praveen Kumar Morum
| Id/create Views | Praveen Kumar Morum
| Initial Load Procs | Praveen Kumar Morum
| Support procs | Praveen Kumar Morum
| Error handling | Praveen Kumar Morum
| Log reports | Praveen Kumar Morum
| Unit Testing | Praveen Kumar Morum
Java
| Design | Zinda
| Properties file - design | Zinda
| Number generation algorithm | Zinda
| Generate numbers | Zinda
| Load generated numbers | Zinda
| Unit Testing (include Subsequent number generations) | Zinda
MQ
| Configurations | Ranjit
| tree | Ranjit
| publish/subscribe | Ranjit
| Exceptions | Ranjit
Testing
| Login | Anand Patil
| Search | Anand Patil
| ownership add/update/delete | Anand Patil
| address add/update/delete | Anand Patil
| phone add/update/delete | Anand Patil
| email add/update/delete | Anand Patil
| membership add/update/delete | Anand Patil
| OBL add/update/delete | Anand Patil
| Link/Unlink | Anand Patil
| Join/Unjoin | Anand Patil
| Exception Scenarios | Anand Patil
| Notifications | Anand Patil
| Audit Log/reporting | Anand Patil
Deployment
UAT
Support