## Test Execution Summary Report
Feature/Components | # Tests Planned | # Tests Passed | # Tests Failed | # Deferred/ blocked | % Tests Executed | Remarks
Functional Test Full Site (FS) | 111 | 103 |  | 8 | 92.79% | 8 Test cases are blocked, waiting for more information from IBM on Action Buttons
Functional Test Language | 60 | 60 |  |  | 100%
Batch Jobs | 5 | 5 |  |  | 100%
Russia Complexity | 12 | 8 |  | 4 | 66.67% | 4 Test cases are blocked, waiting for more information from IBM on Action Buttons
Browser Compatibility | 30 | 30 |  |  | 100%
Platform Testing Test New Web Portal | 5 | 5 |  |  | 100%
Total | 223 | 211 |  | 12 | 94.62%

## Defect Summary Report
Status | 1 – Critical | 2 – High | 3 – Medium | 4 – Low | Total
Submitted
Assigned |  |  | 1 |  | 1
Implemented |  |  | 1 |  | 1
Integrated
Postponed |  |  | 1 |  | 1
Verfified
Closed |  | 10 | 25 | 13 | 48
Duplicate |  | 1 |  |  | 1
Rejected |  | 1 | 4 | 2 | 7
Deffered
More Info
Total |  | 12 | 32 | 15 | 59

## Defects
Defect ID | Headline | State | Priority | Comments
IKEA00918009 | JST: Incorrect search results when the Keyword Search is performed twice with separate keywords | Closed | 2 - High
IKEA00917916 | JST: First Keyword Search Then Filter Based Search - Search Result displays Jobs based on Keyword Search Only | Closed | 2 - High
IKEA00918012 | JST: Filter criteria not working for Job Type field | Closed | 2 - High
IKEA00918013 | JST: Filter criteria not working for Language field | Closed | 2 - High
IKEA00917942 | JST: Burlington Location is not displayed as one of the options for Canada | Closed | 3 - Medium
IKEA00918007 | JST: Sorting Doesn't work on Job Title Work Area and Date updated Columns | Closed | 3 - Medium
IKEA00918011 | JST: Dynamic updation of # jobs found | Closed | 3 - Medium
IKEA00917974 | JST: 54 jobs found is displayed by default when the Job Search Page Loads | Closed | 3 - Medium
IKEA00918008 | JST: Spell Errors in Job Search Page | Closed | 4 - Low
IKEA00918363 | JST: Text below 5 buttons in Search Result is missing | Closed | 4 - Low
IKEA00918354 | JST: Cookie policy and Terms of Use hyperlinks are centre aligned and are not underlined | Closed | 4 - Low
IKEA00918010 | JST: Countries in Country List is not listed in alphabetical ascending order | Closed | 4 - Low
IKEA00917860 | JST: Scroll Bar not working when user navigates to the available option using down arrow key on the key board for any of the fields | Closed | 4 - Low
IKEA00917953 | JST: Mexico Status is Inactive as per Job Search tool fields spreadsheet but still displayed as one of the option in Country field. | Closed | 4 - Low
IKEA00917959 | JST: User is able to select Czech Language twice. | Rejected | 4 - Low
IKEA00921948 | JST: With New Deployment, To clear Browser cache we need to hit Ctrl + F5, to reload the new version of static files | Assigned | 3 - Medium | Static Files to be cleared before deploying to production
IKEA00921054 | JST: Batch Job Import Job Inserted Junk Values in Job Title Column of JOB_INFO Table | Implemented | 3 - Medium | This defect is to be verified during jobs sync Batch Job in SIT
IKEA00921173 | JST: jobsInfoUpdateBatchJobId Job not marking jobs as Inactive not updating Created On, Created By and Modified By columns in Job InfoTable | Postponed | 3 - Medium | This defect is to be tested during Batch Jobs in SIT
IKEA00919144 | JST: No matching records found message when the result is sorted based on Job Title after doing Keyword Search | Closed | 2 - High
IKEA00919062 | JST: You can either select Russia or non Russia jobs at the same time error message when Blank Keyword Search is made for first time | Closed | 2 - High
IKEA00919956 | JST: Notification not displayed when Russian and Non Russian Jobs are selected together | Closed | 2 - High
IKEA00919152 | JST: jstresultsection.bottomtxt - The text should not be displayed when any job related to Russia is selected | Closed | 2 - High
IKEA00918608 | JST: Inconsistency in the Job Search URL | Closed | 2 - High
IKEA00918964 | JST: Country, Location, Workarea and Language is displayed in English for Russia | Closed | 2 - High
IKEA00919281 | JST: Junk Dates displayed 3916-03-12 | Closed | 3 - Medium
IKEA00920448 | JST: More than 10 rows are displayed in Russia Job Search Results when Keyword search is made | Closed | 3 - Medium
IKEA00921950 | JST: Inconsistent search results with keyword search | Closed | 3 - Medium
IKEA00920337 | JST: Back to Job Search Button missing in Log in to candidate profile page | Closed | 3 - Medium
IKEA00919581 | JST: Search result Date updated column Date Format not consistent in Keyword and rest of Filter Search | Closed | 3 - Medium
IKEA00921756 | JST: Clear Filter Should Clear the Keyword Pattern Entered By User | Closed | 3 - Medium
IKEA00921222 | JST: Work Area Code Language Code in Job Info table is Null for few Work Area And Language | Closed | 3 - Medium
IKEA00922210 | JST: Device Testing - Back to Job Search not retaining the filter criteria set | Closed | 3 - Medium
IKEA00920297 | JST: The application has encountered an unknown error message when the Pagination Hyperlinks is clicked simultaneously and very fast | Closed | 3 - Medium
IKEA00919646 | JST: Auto Completion - When user keys in value "U", then all the options that has the character "U anywhere in the word should be displayed as an option | Closed | 3 - Medium
IKEA00920293 | JST: Back to Search - The filter criteria set and the Search Result before viewing the Job Details not retained | Closed | 3 - Medium
IKEA00921827 | JST: Action buttons Create search agent and Save to basket and Search Results Botton Text hidden even when no Russian Job is selected | Closed | 3 - Medium
IKEA00918773 | JST: Drop Down to select number of records to be shown per page should be removed | Closed | 3 - Medium
IKEA00920013 | JST: Keyword search for Special characters doesn't yield correct result | Closed | 3 - Medium
IKEA00920509 | JST: 2 User should not be able to execute 2 Batch jobs simultaneously | Closed | 3 - Medium
IKEA00919685 | JST: Min and Max Characters that can be entered in Text Boxes is not Limited to 100 | Closed | 3 - Medium
IKEA00921027 | JST: Job Type And Language and Internal External Job Details not imported while executing Batch Jobs | Closed | 3 - Medium
IKEA00920805 | JST: page.title is set to JOB SUCHE for Switzerland - German Locale (CH_de) But the Page TItle is displayed as JOB SEARCH | Closed | 3 - Medium
IKEA00920277 | JST: Search for Filter with Language - English(US) Or English(Intl) - returns with No matching records found message | Closed | 3 - Medium
IKEA00922897 | JST: Action Buttons Create search agent and Save to basket are hidden even when no Jobs are Selected | Closed | 3 - Medium
IKEA00919254 | JST: Dynamic updation of # jobs found not done when Clear filters button is clicked | Closed | 3 - Medium
IKEA00918968 | JST: Advanced Search and Log in to candidate profile hyperlinks are appearing on the left hand side | Closed | 4 - Low
IKEA00919524 | JST: Auto Completion - When user keys in value "U", then all the options that has the character "U anywhere in the word should be displayed as an option | Closed | 4 - Low
IKEA00918549 | JST: Blank Keyword Search results in No matching records found | Closed | 4 - Low
IKEA00921233 | JST: jobsInfoPopulateBatchJobId Job not updating Created On, Created By and Modified By columns in Job Info Table | Closed | 4 - Low
IKEA00918573 | JST: Text Job type should be displayed in grey when no option is selected for the field | Closed | 4 - Low
IKEA00922898 | JST: Clear Filter Button Label is not displayed completely since the Clear Filter Text Translation in Russian is too long | Closed | 4 - Low
IKEA00920513 | JST: Batch Job log files are created outside logs folder instead of creating inside logs folder | Closed | 4 - Low
IKEA00919955 | JST: 2 Action Buttons and jstresultsection.bottomtxt Property Value Displayed When a Russian Job is Selected in Search Results | Duplicate | 2 - High
IKEA00919119 | JST: Keyword Search not working for Switzerland de, fr and it and Russia ru Locales | Rejected | 2 - High
IKEA00919689 | JST: Job Search Page Not Displayed as Correctly in Internet Explorer Version 11 When opened using Wireframe | Rejected | 3 - Medium
IKEA00919990 | JST: Search Results displays No matching records found if specific sequence of steps are performed | Rejected | 3 - Medium
IKEA00919220 | JST: Job Search Page layout in Safari Browser is as per Wireframe | Rejected | 3 - Medium
IKEA00919073 | JST: Internationalization / Property File not working for Switzerland with German Language | Rejected | 3 - Medium
IKEA00921215 | JST: Horizontal Scroll Bar in Search Results section | Rejected | 4 - Low