## Sheet1
Skill Area | Task | Possible Resources | Effort/Duration(In Hr's) | Dependency | Sprint
UI/Angular
| Screen design | Basavaraj | 16
| Build Screens | Basavaraj | 48
| login | Basavaraj | 16
| search | Basavaraj | 48
| main | Basavaraj | 48
| address change | Basavaraj | 24
| email change | Basavaraj | 24
| phone change | Basavaraj | 24
| join | Basavaraj | 54
| unjoin | Basavaraj | 16
| link | Basavaraj | 16
| unlink | Basavaraj | 16
| Validations | Basavaraj | 80
| Error handling | Basavaraj | 80
| invoke spring APIs | Basavaraj | 80
| Unit Testing | Basavaraj | 80
SOLR
| design | Zinda,ranjit,Basavaraj | 8
| Indexing - initial load | Zinda,ranjit,Basavaraj | 8
| indexing - delta changes/CDC | Zinda,ranjit,Basavaraj | 12
| Integrating with UI | Zinda,ranjit,Basavaraj | 12
| Unit Testing | Zinda,ranjit,Basavaraj | 10
Spring/Spring Boot
| APIs for UI() | Ranjit, Zinda,Shyam | 160
| APIs for MuleSoft |  | Need to clarify
| DB updates using Hybernate | Ranjit, Zinda,Shyam | 120
| Publish to MQ |  | Need to clarify
| Transaction Manager | Ranjit, Zinda,Shyam | 80
| Error Handling | Ranjit, Zinda,Shyam | 100
| Monitoring CDC | Ranjit, Zinda,Shyam | Need to clarify
| Processing CDC records | Ranjit, Zinda,Shyam | Need to clarify
| ownership add/update/delete | Ranjit, Zinda,Shyam | 24
| address add/update/delete | Ranjit, Zinda,Shyam | 24
| phone add/update/delete | Ranjit, Zinda,Shyam | 24
| email add/update/delete | Ranjit, Zinda,Shyam | 48
| membership add/update/delete | Ranjit, Zinda,Shyam | 48
| obl add/update/delete | Ranjit, Zinda,Shyam | Need to clarify
| link/unlink | Ranjit, Zinda,Shyam | 60
| join/unjoin | Ranjit, Zinda,Shyam | 60
| Unit Testing | Ranjit, Zinda,Shyam | 120
Hibernate
| design | Ranjit, Zinda,Shyam | 24
| Build Objects | Ranjit, Zinda,Shyam | 24
| ownership | Ranjit, Zinda,Shyam | 24
| address | Ranjit, Zinda,Shyam | 24
| email | Ranjit, Zinda,Shyam | 24
| phone | Ranjit, Zinda,Shyam | 24
| membership | Ranjit, Zinda,Shyam | 24
| OBL | Ranjit, Zinda,Shyam | 24
| Stging tables for delta updates/CDC | Ranjit, Zinda,Shyam | 24
| Unit Testing | Ranjit, Zinda,Shyam | 120
MuleSoft
| RAML design | Ashish | 32
| API Gateway Configuration | Ashish | 28
| MQ Subscription and Routing flow | Ashish | 40
| MQ Publishing flow | Ashish | 32
| TSW ownership add/update/delete | Ashish | 36
| TSW address add/update/delete | Ashish | 36
| TSW phone add/update/delete | Ashish | 36
| TSW email add/update/delete | Ashish | 36
| TSW membership add/update/delete | Ashish | 36
| OBL add/update/delete | Ashish | 16
| Universe customer add / update / delete | Ashish | 32
| Universe customer Address add / update / delete | Ashish | 30
| Universe customer Phone add / update / delete | Ashish | 30
| Universe customer Email add / update / delete | Ashish | 30
| Universe customer Membership add / update / delete | Ashish | 30
| Universe Join/Unjoin | Ashish | 40
| Univese Link/Unlik | Ashish | 36
| TSW feed to CIE | Ashish | 32
| TSW Augmentation | Ashish | 40
| SSL Configuration | Ashish | 40
| Caching | Ashish | 16
| Universe feed to CIE | Ashish | 36
| CIE Feed to Solr | Ashish | 40
| Notification API for creating ticket | Ashish | 40
| Critical logging | Ashish | 16
| Exception handling | Ashish | 40
| Unit Testing | Ashish | 45
| Integration Testing | Ashish | 60
Database
| create table scripts | Praveen Kumar Morum | 2
| design/create other DB objects (views, triggers, synonyms, indexes/constraints) | Praveen Kumar Morum | 32
| Create core tables | Praveen Kumar Morum | 2
| Create staging tables | Praveen Kumar Morum | 2
| create mapping tables | Praveen Kumar Morum | 2
| Load mapping tables | Praveen Kumar Morum | 12
| Load unique ids | Praveen Kumar Morum | 20
| Id/create Views | Praveen Kumar Morum | 15
| Initial Load Procs | Praveen Kumar Morum | 180
| Support procs | Praveen Kumar Morum | 200
| Error handling | Praveen Kumar Morum | 20
| Log reports | Praveen Kumar Morum | 20
| Unit Testing | Praveen Kumar Morum | 80
Java
| Design | Zinda
| Properties file - design | Zinda | 16
| Number generation algorithm | Zinda | 24
| Generate numbers | Zinda | 8
| Load generated numbers | Zinda | 32
| Unit Testing (include Subsequent number generations) | Zinda | 24
MQ
| Configurations | Ranjit | 10
| tree | Ranjit | 15
| publish/subscribe | Ranjit | 20
| Exceptions | Ranjit | 8
Testing
| Login | Anand Patil | 8
| Search | Anand Patil | 16
| ownership add/update/delete | Anand Patil | 16
| address add/update/delete | Anand Patil | 16
| phone add/update/delete | Anand Patil | 16
| email add/update/delete | Anand Patil | 16
| membership add/update/delete | Anand Patil | 16
| OBL add/update/delete | Anand Patil | 16
| Link/Unlink | Anand Patil | 16
| Join/Unjoin | Anand Patil | 16
| Exception Scenarios | Anand Patil | 16
| Notifications | Anand Patil | 16
| Audit Log/reporting | Anand Patil | 32
| API Gateway | Anand Patil | 80
| Indixing SOLR | Anand Patil | 80
| DB Testing | Anand Patil | 80
Deployment
UAT
Support

## Sprint 1
Skill Area | Task | Possible Resources | Effort/Duration(In Hr's) | Dependency | Sprint
UI/Angular
| Screen design | Basavaraj
| login | Basavaraj
| search | Basavaraj
| Validations | Basavaraj
| Unit Testing | Basavaraj
SOLR
| Analysis for Indexing Search | Zinda,ranjit,Basavaraj
Spring/Spring Boot
| APIs for UI() | Ranjit, Zinda
| APIs for MuleSoft | Ranjit, Zinda
| Unit Testing | Ranjit, Zinda
Hibernate
| design | Ranjit, Zinda
| Build Objects | Ranjit, Zinda
| Unit Testing | Ranjit, Zinda
Database
| create table scripts | Praveen Kumar Morum
| Create core tables | Praveen Kumar Morum
| Create staging tables | Praveen Kumar Morum
| create mapping tables | Praveen Kumar Morum
| Load Country and State province mapping tables | Praveen Kumar Morum
| Initial Load of UV Data into Ownership_account Table | Praveen Kumar Morum
| Unit Testing | Praveen Kumar Morum
Java
| Design | Zinda
| Pseduo RandomNumber generation algorithm | Zinda
| Check Digit Algorithm | Zinda
| CIE Unique ID generation | Zinda
| Properties file - design | Zinda
| Load generated CIE unique IDs into proerty file | Zinda
| Applying Regular Expression | Zinda
| Unit Testing (include Subsequent number generations) | Zinda
MQ
| Configurations | Ranjit
| tree | Ranjit
| publish to IBM Exchange queue | Ranjit
Testing
| Login | Anand Patil
| Search | Anand Patil
| CIE Unique ID testing | Anand Patil
| DB Testing on Mapping data and Universe data | Anand Patil